## Sheet1
Deliverable Cadence	Description of Deliverable	Duration / (hours or days)	Projected Start Date	Anticipated End Date
1A	Meeting with Customer IT Department	1 day	01/06/2020	01/06/2020
1B	Lab walk through	1 day	01/07/2020	01/07/2020
1C	Gather details on network/Physical Hardware	2 days	01/08/2020	01/09/2020
1D	Remote Access Setup	2 days	01/10/2020	01/13/2020
2A	Virtual Machine Reservation	2 days	01/14/2020	01/15/2020
2B	Machine Setup	4 days	01/16/2020	01/21/2020
2C	Operating System Setup	3 days	01/22/2020	01/24/2020
3A	Nagios Deployment	4 days	01/27/2020	01/30/2020
3B	Testing and Review	5 days	01/31/2020	02/06/2020
4A	Deployment Training	5 days	02/07/2020	02/13/2020
4B	Customer Handoff / Question Review	5 days	02/14/2020	02/20/2020